## How to use
Kanban board + flow metrics
Free template by Kanban.Global · kanban.global/en/modelos-kanban
1. Board tab: adapt the columns to your flow and set a WIP limit per stage ("WIP limit" row). The count turns red when the limit is exceeded.
2. Items tab: log each item with the date the team committed to it (Start) and the delivery date (Done). Cycle time and age are calculated.
3. Metrics tab: weekly throughput, cycle time p50 and p85, current WIP and a suggested service level expectation (SLE).
4. For a scatterplot, histogram and Monte Carlo forecast, export the Items tab as CSV and upload it at kanban.global/en/analisar.
Golden rules: stop starting, start finishing; a blocked item still counts toward WIP; measure from commitment, not from the idea.

## Board
Kanban board + flow metrics
Backlog | Ready to pull | Doing | Review | Done
| 5 | 3 | 2 |  | ← WIP limit
← Items now
Customer survey (backlog) |  | K-010 · Contract review | K-011 · Sales dashboard | K-001 · Pricing page
|  | K-012 · Customer survey |  | K-002 · ERP integration
K-003 · Checkout fix
K-004 · Monthly report
K-005 · New onboarding
K-006 · Permission changes
K-007 · Database migration
K-008 · October campaign
K-009 · Partner API

## Items
ID | Item | Class of service | Start (commitment) | Done (delivery) | Cycle time (days) | Age (days, in progress) | Delivery week
K-001 | Pricing page | Standard | 2026-08-03 | 2026-08-07
K-002 | ERP integration | Standard | 2026-08-04 | 2026-08-12
K-003 | Checkout fix | Expedite | 2026-08-06 | 2026-08-08
K-004 | Monthly report | Standard | 2026-08-08 | 2026-08-15
K-005 | New onboarding | Fixed date | 2026-08-11 | 2026-08-14
K-006 | Permission changes | Standard | 2026-08-13 | 2026-08-19
K-007 | Database migration | Standard | 2026-08-15 | 2026-08-18
K-008 | October campaign | Fixed date | 2026-08-18 | 2026-08-25
K-009 | Partner API | Standard | 2026-08-21 | 2026-08-24
K-010 | Contract review | Standard | 2026-08-27
K-011 | Sales dashboard | Intangible | 2026-08-30
K-012 | Customer survey | Standard | 2026-09-02
Formulas:
Age (days, in progress) = IF(AND([Start (commitment)]<>"",[Done (delivery)]=""),TODAY()-[Start (commitment)]+1,"")

## Metrics
Flow metrics
Throughput per week
Items done | Week | Delivered
Average cycle time (days)
Cycle time p50 (days)
Cycle time p85 (days)
Current WIP (items in progress)
Suggested SLE
4. For a scatterplot, histogram and Monte Carlo forecast, export the Items tab as CSV and upload it at kanban.global/en/analisar.